## Template
Implementation Checklist
Task | Date | Cultivation/Legacy Conversations | Marketing | Stewardship | Org Culture | Team member responsible | Completed
January
February
March
April
May
June
July
August
September
October
November
December

## Example
Implementation Checklist
Task | Date | Cultivation/Legacy Conversations | Marketing | Stewardship | Org Culture | Team member responsible | Completed
January
Present at board meeting |  | x |  |  |  | ED and development director | 1/9
Have 2 legacy conversations |  | x |  |  |  | ED and board chair | 1/8, 1/27
Ask Donor 1 to do a testimonial for Feb newsletter |  |  | x | x |  | board chair | 1/22
Announce legacy society in monthly enewsletter |  |  | x |  |  | development director | 1/12
Calls/thank you notes |  |  |  | x |  | board chair, development director | ongoing
February
Publish Donor 1 testimonial in newsletter |  |  | x |  |  | development director | 2/9
Facebook post with Donor 1 testimonial |  |  | x |  |  | development associate
Prepare legacy society ad for March newsletter |  |  | x |  |  | development associate
Have 3 legacy conversations |  | x |  |  |  | development director, board chair, ED
Calls/thank you notes |  |  |  | x |  | development director, board chair, ED
March
Publish legacy society ad in newsletter |  |  | x
Work with designer to create legacy society ribbons for donor events |  |  | x | x
Calls/thank you notes |  |  |  | x
April
Donor event with legacy society ribbons |  |  | x | x
After donor event, have 3 legacy conversations |  | x
Calls/thank you notes |  |  |  | x
May
Prepare Donor 2 testimonial - video |  |  | x | x
Write annual report blurb about launch of endowment and legacy society |  |  | x
Finalize list of legacy society members for annual report |  |  | x | x
Calls/thank you notes |  |  |  | x
June
Annual legacy society event |  |  |  | x
Facebook post about annual legacy society event, include Donor 2 video testimonial |  |  | x
Calls/thank you notes |  |  |  | x
July
Send copy of annual report to each legacy society member with handwritten note |  |  |  | x
Have 2 legacy conversations |  | x
Calls/thank you notes |  |  |  | x
August
Work with Communications to add legacy society and planned giving section to website |  |  | x
Review conversations from past 6 months - follow up as necessary |  | x
Calls/thank you notes |  |  |  | x
September
Working on website |  |  | x
Have 2 legacy conversations |  | x
Calls/thank you notes |  |  |  | x
October
Go live on website |  |  | x
Board presentation, round 2 - present this year's progress |  | x
Follow up board presentation with one-on-one meetings |  | x
Calls/thank you notes |  |  |  | x
November
Continue board one-on-ones |  | x
Calls/thank you notes |  |  |  | x
December
Holiday cards to each legacy society members signed by board pres, ED, and key staff |  |  |  | x
Calls/thank you notes |  |  |  | x